## Plan of action
| Deliverable | Description | Owner | Date | Action
1 | Questionnaire | Completed response to the accompanying Agentic Framework Questionnaire (Excel) | Multiple |  | Phil is looking for resource to populate the responses
2 | Written Response | Long-form narrative response addressing each section of this brief, including your vision for our partnership | James / Kalai |  | Kicking this off today
3 | Enterprise Architecture Diagram | Visual diagram showing how your framework integrates with our enterprise architecture (M365, Power Platform, Okta, multi-cloud, business systems): including where the Control Plane surface sits | Kalai
4 | C4 Architecture Diagrams | First three layers (Context, Container, Component) for your proposed solution | Kalai
5 | POC 1: Solution Architecture & Design | Proposed architecture per Addendum A, including Control Plane design | Owner of PoC |  | Phil is looking for resource to populate the responses Who wons the technical detail
6 | POC 2: Solution Architecture & Design | Proposed architecture per Addendum B, including Control Plane design | Owner of PoC |  | Phil is looking for resource to populate the responses Who wons the technical detail
7 | PRD for Each POC | Product Requirements Document for each use-case demonstrating your understanding of the brief | Owner of PoC |  | Phil is looking for resource to populate the responses Who wons the technical detail
8 | NFR Response | Response to the NFR baseline table in §5.4: GA/preview/roadmap per item
9 | High-Level Delivery Plan | Timeline, milestones, team composition, and dependencies for both POCs | Maybe EY / what's the role
10 | Commercial Proposal | Licensing model, TCO breakdown (per NFR scale tiers in §5.4), and partnership terms | Marta / Steve
11 | Customer Testimonials & References | (a) Written testimonials from 3 enterprise customers using your agentic framework at scale. | Kalai / Olga / Steve / James
(b) Reference contacts: 3 customers available for direct calls, each with an Engineering Lead, AI/ML Ops Lead, and Head of Transformation (SVP+). References should be organisations of comparable scale and complexity to WPP.
12 | Package the response / make it look mega
13 | Capture questions | Friday call - 1pm
10th April ISD v E&Y roles defined
15th April Q&A questions
17th April differentiators defined against other competitors
17th April Consumption plan completed
21st Commercial terms defined
23rd written response
Clear the diaries for the next 10 days to fully focus on the RFP: a) Bigger picture / vision - > Kalai & James (this week and revise next week) b) Technical team align to the vision, find a resource - > Phil & Alex (this week and revise next week) c) Product group advise and support - Kalai & James d) E&Y deep dive into key references Nokia - > Marta & Olga (today) e) Align with E&Y & ISD - what are the roles - > Marta (this week) f) Call with Tom and his team - Friday

## RFP-Response Team
Name | Role